## Sheet1
CommunicationDate | CommunicationType | USFWS_RegionalLeadOffice | USFWSParticipantName | USAG_DirectorateLead | USAG_ParticipantName | Subject | Action Items | Notes
2020-07-31 | Email | NA | NA | POM DPW-E | April Andujar | HDR Draft Agency INRMP Development notificiation |  | Sent from Kate Crosthwaite
2020-09-15 | Meeting-Teams | NA | NA | POM DPW-E | April Andujar | INRMP Revision Internal Kickoff Meeting
2020-09-15 | Meeting-Teams | NA | NA | POM DPW-E | April Andujar | INRMP Revision Purpose and Process |  | HDR, USACE
2020-12-14 | Email | Ventura | Mark Ogonowski | POM DPW-E | April Andujar | PoM INRMP Revision Announcement & schedule meeting |  | Hello Mark and Leilani, The Presidio of Monterey is developing a major revision to our Integrated Natural Resource Plan, under contract with HDR. We are hoping to schedule a meeting with the external stakeholders in early January. Originally we hoped to have this meeting in person, however Covid travel restrictions prohibit that. We have been using MS Teams for meeting where presentations and/or document sharing are needed. Does this format work for you? Please let me know what your availability is in the first 2 weeks of January. April
2020-12-15 | Email | Ventura | Mark Ogonowski | POM DPW-E | April Andujar | Presidio of Monterey INRMP meeting - scheduling |  | Hi April, Thanks for getting in touch regarding your INRMP revision. Leilani is on leave for the remainder of 2020 and will be back in the office the first week of January; I'm acting for her during that time but I may not be the lead biologist for this project. I have access to Leilani's calendar and can provide some potential dates that seem to work for her, though it would probably be best if you have flexibility at your end to wait until Leilani returns so she can schedule directly with you. If it is urgent from your end let me know, we want to accommodate your process as best we can and I'll float you some dates during the first two weeks of January that appear open for Leilani. (I think we'll still need to consider any meeting scheduled now to be tentative -- please accept my apologies for that). MS Teams is our standard platform for online meetings so that will work fine.
2020-12-17 | Email | Ventura | Mark Ogonowski | POM DPW-E | April Andujar | Presidio of Monterey INRMP meeting - scheduling |  | Hi April, The following blocks currently appear open for Leilani during the week of January 11-15: 1/11 -- 10-12, 1-5 1/12 -- 11-12, 1-2. 1/13 -- 1-2:30 1/14 -- 1-5. Leilani won't respond until the week of January 4th but hopefully the tentative date you set will end up working for her. I didn't include my availability though I may be able to join the call if Leilani thinks I should and I'm not sure about Todd's availability, but please include Todd and myself on the invite. Thanks for your understanding regarding our scheduling needs. -Mark
2020-12-17 | Email | Ventura | Mark Ogonowski | POM DPW-E | April Andujar | Presidio of Monterey INRMP meeting - scheduling |  | Hi Mark, If you could look at availability for the week of Jan 11-15, I would appreciate it. I would like to get something on the calendar soon, even if it's tentative. The meeting will be for 1 hour. Thanks, April
2020-12-28 | Email | Ventura | Mark Ogonowski | POM DPW-E | April Andujar | Presidio of Monterey INRMP meeting - scheduling |  | Hi Mark, We would like to schedule for January 14th at 1300. Once Leilani returns from leave and confirms that time, I will send out the MS Teams calendar invite. April
2021-01-01 | Meeting-Teams | Ventura | Leilani, Joseph, Todd | POM DPW-E | April Andujar |  |  | CDFW, City of Monterey, USACE, North Bay Industries, Sunik Properties, US Navy, US Army, CA Military Dept, HDR
2021-01-07 | Email | Ventura | Leilani Takano | POM DPW-E | April Andujar | Presidio of Monterey INRMP meeting - scheduling |  | Hi Leilani, Thanks for getting back to me. I hope you had a relaxing holiday break. I have sent the MS Teams invite. Sometimes with outside agencies, people get an error message. If you experience any problems or don’t get the invite please let me know. April
2021-01-07 | Email | Ventura | Leilani Takano | POM DPW-E | April Andujar | Presidio of Monterey INRMP meeting - scheduling |  | Hi April, Thank you for your patience. I've been trying my best to quickly catch up on emails. I am available at 1pm on the 14th. Leilani
2021-01-07 | Email | Ventura | Leilani Takano | POM DPW-E | April Andujar | Presidio of Monterey INRMP meeting - scheduling |  | Hi Leilani and Mark, I'm just checking in to see if the 14th at 1300 will still work for the INRMP meeting? Thanks,
2021-01-07 | Email | Ventura | Mark Ogonowski | POM DPW-E | April Andujar | Presidio of Monterey INRMP meeting - scheduling |  | Hi April, That time still works for me. As I mentioned previously, Leilani is more essential to this conversation than I, so please prioritize scheduling that works for her. Thank you. Mark - SENIOR FISH & WILDLIFE BIOLOGIST
2021-01-11 | Email | Ventura | Leilani Takano | POM DPW-E | April Andujar | Presidio of Monterey INRMP meeting - scheduling |  | Hi April, Can you please send the meeting invite to Joseph Brandt (copied on this email) and remove Mark Ogonowski from the calendar invite? If there is any background information that Joseph and I would benefit from prior to the meeting, can you please send it to us via email? Thank you and we look forward to meeting with you, Leilani
2021-05-26 | Email | Ventura | Joseph Brandt | POM DPW-E | April Andujar | PoM INRMP Meeting - USFWS inquiry on INRMP Statust | April to follow up with USFWS re: update | Email from Joseph: Hello April, It has been a while so I thought I would reach out to see how the INRMP development is going at Presidio at Monterey. Since your initial presentation about INRMP I was able to touch base with Todd Lemein about Yadon's piperia a what might be a good conservation strategy in the INRMP for this species. I'd be happy to set up a time for the three of us to discuss. I also reached out to a friend who manage natural resources for the Navy Bases of Ventura County to get a sense of sort of funding opportunities might be available to you to assist in implementing the INRMP. We could compare notes on that as well. I'd really like to be a resource for you as you are working on developing your conservation goals. I also wanted to ask if it was possible to get a copy of the presentation you gave us just so I have a better understanding of all the properties you manage.
2021-11-12 | Email | NA | NA | POM DPW-E | April Andujar | HDR submittal of draft INRMP w/ USAG, USAECcomment response matrix to USAG PoM via DoD SAFE | April to send draft INRMP & comment matrix to USFWS, CDFW
2021-11-16 | Email | Ventura | Steve Henry | POM DPW-E | April Andujar | USAG PoM Section 7 Consultation: Biological Assessment |  | Notification that April's last day is Dec 05 2021
2021-11-17 | Email | Ventura | Leilani Takano | POM DPW-E | April Andujar | PoM Section 7 Consultation - INRMP PBA |  | Good Morning Leilani, Thank you the quick response and congrats. I had just emailed Joseph to send the INRMP for review and signature. It’s a large document so it would be best to send via our safe site, however the link expires in 2 weeks. Should I sent it to you for storage until Joseph returns or it’s assigned to someone else? With my departure, the only other biologist on staff with the Presidio Complex is Patty Goodman. She is serving at our satellite location at Camp Roberts, and has limited familiarity with the species we manage here, so the contractor is the most knowledgeable. The contract that supports this INRMP and PBA ends at the end of January, so we really need to have completion no later than that. Given the long lead times for hiring actions, my replacement likely won’t be here until mid-summer. The irony of this situation is that the delay in the HQ review was partly due to the position that I’m going to being vacant since April. Having the new INRMP and BO completed will help insure compliance with the TES management and the NEPA Program Mgr (Joelle Lobo) will have better clarity on what actions would require consultation.
2021-11-17 | Email | Ventura | Joseph Brandt | POM DPW-E | April Andujar | PoM INRMP Meeting - updated on review |  | My (Joseph) detail won't be finished until the end of Feb. If you can how about we check in after the new year. I may have some availability to meet before my detail officially ends but won't know until we are closer to next year.
2021-11-17 | Email | Ventura | Joseph Brandt | POM DPW-E | April Andujar | PoM INRMP Meeting - NR Prg Mgr position |  | Email from April: Yes my position will be filled, it will likely take 4-6 months before they are onboard. Of course that’s if we don’t have a shutdown, which would delay things even more! The Army is transferring to O365 so all email addresses will be @army.mil instead of @mail.mil. Will you be finished with your detail by January? Did you want to put something on the calendar now? I’ll get the INRMP sent out today. Note- it won’t have my name in the from line- it will be a noreply address.
2021-11-17 | Email | Ventura | Joseph Brandt | POM DPW-E | April Andujar | PoM INRMP Meeting - Update & NR Prg Mgr position |  | Email from April: Hi Joseph, The INRMP has finally finished undergoing legal and technical review. We had originally planned to do a follow up meeting to present the INRMP, however I’m leaving for a new position in just a few weeks. I’m going to a Natural Resource support position at our Headquarters in San Antonio, so I will be available for questions. I just won’t have computer access for several weeks (probably not until the beginning of the year). If you do want to schedule a meeting before the end of the month, please let me know. Otherwise, I will just send the INRMP and request a comment matrix be completed for any comments. I can send you the INRMP via the safe site (it’s a large file), who all should I include on that distribution?
2022-01-06 | Email | NA | NA | POM DPW-E | Tania Leisten | USACE FY20 HDR Contract POP Extension W9127820F0190 |  | Email from Tania to HDR: Clarifying that HDR/USAG POM needs comments by to the 29th so they can be incorporated, or is the 29th when the contract ends and we need the comments back well before that so they can be incorporated. I am going to send an email to FWS to see their projection on completing their review of the INRMP. I'd like to give them a drop dead date to see if they can meet it.
2022-01-07 | Email | NA | NA | POM DPW-E | Tania Leisten | HDR FY21 Task Order POP Extension & USFWS Comments | Follow up with USFWS re: comment timeline | Email from Kate: The contract's period of performance (end date) is 29 January 2022 - so, receipt of comments well before the 29th would be necessary unless comments are exceptionally minimal and do not require staffing internally on your end. The INRMP and Biological Assessment are the documents under review.
2022-01-07 | Email | NA | NA | POM DPW-E | Tania Leisten | USACE FY20 HDR Contract POP Extension W9127820F0190 |  | Email from HDR Kate C.: The contract's period of performance (end date) is 29 January 2022 - so, receipt of comments well before the 29th would be necessary unless comments are exceptionally minimal and do not require staffing internally on your end. The INRMP and Biological Assessment are the documents under review.
2022-01-14 | Email | NA | NA | POM DPW-E | Tania Leisten | HDR FY21 Task Order POP Extension & USFWS Comments |  | Email from Tania to HDR: So (USFWS) replied indicating that January and February are very busy and he would be unable to process the review before the 29th. I asked for an estimation on when he might have it done, but I haven't received a response back. I don't have a status on USFWS. They might be longer. I'm not sure what we do from here, but I presume if the comments are significant we can finish the document in house. Any thoughts?
2022-01-25 | Email | NA | NA | POM DPW-E | Tania Leisten | USACE FY20 HDR Contract POP Extension W9127820F0190 |  | Email from HDR kate C.: We recommend a POP extension to support the completion of the INRMP and BA to allow for time to address comments expected from regulatory agencies. I expect that no word has been received from USFWS or CDFW at this time.
2022-02-07 | Letter-Digital | NA | NA | POM DPW-E | Tania Leisten | USACE FY20 HDR Contract POP Extension W9127820F0190 |  | Email from Crystal Darnell: Please see attached fully executed MOD W9127820F0190 to extend PoP for 6 months.
2022-02-17 | Email | Ventura | Leilani Takano | POM DPW-E | Tania Leisten | USAG PoM Section 7 Consultation: INRMP PBA follow up |  | Email from Leilani: I appreciate you extending the contractors timeline to help accommodate much needed time by our agency to review the BA / project. Joseph returns on March 8 from his detail, and I will assign the BA to him then. I do think we can complete a review by June 2022.
2022-02-17 | Email | Ventura | Leilani Takano | POM DPW-E | Tania Leisten | USAG PoM Section 7 Consultation: INRMP PBA follow up |  | Email from Tania: Good Afternoon Leilani, Thank you for the update, we definitely understand resource constraints. We extended our contract period of performance to July that supports this effort, but we are unable to extend it past that date as we cannot spend funds as we are under a continuing resolution. Do you foresee any issues getting comments to us by June? That will give us time to make any edits to the documents before the contract expires. Due to our resource constraints we are dependent on this contract as we do not have the in house resources to wrap this up ourselves after FWS review. We just ask that you consider our constraints as much as possible when prioritizing projects as this could impact mission if not completed within our contract period of performance. We are also here to help, so anything we can do to facilitate the process, please let me know. Thanks Tania
2022-02-17 | Email | Ventura | Leilani Takano | POM DPW-E | Tania Leisten | USAG PoM Section 7 Consultation: INRMP PBA comments |  | Email from Leilani: I want to formalize my email below with what our office has been calling an "unassigned letter". Please see attached. Unfortunately, we've had recent turnover and due to a limited capacity, I haven't been able to assign the subject consultation to someone on our staff. Joseph Brandt is on a detail assignment with our regional office since mid-Nov. until March 4. As you may know, Joseph has been assigned our office's lead for support or review of Presidio of Monterey projects, including section 7 consultations. When he returns, I will assign the subject consultation to him.
2022-03-22 | Email | Ventura | Leilani Takano | POM DPW-E | Tania Leisten | USAG PoM Section 7 Consultation: INRMP PBA follow up |  | Good Afternoon Leilani, I just wanted to touch base and see if we were still on track for getting a completed review by June? This would include the INRMP and BA. Thank you, Tania
2022-03-25 | Email | Ventura | Leilani Takano | POM DPW-E | Tania Leisten | USAG PoM Section 7 Consultation: INRMP PBA Comments | USAG PoM Section 7 Consultation: INRMP PBA Comments | Thank you for reaching out. Yes, we expect to provide you our comments on the INRMP and PBA by June. I have copied Joseph Brandt, Senior Biologist, who is the lead in the review of the two documents. If you have any additional questions, please feel free to reach out to him directly.
2022-05-27 | Email | Ventura | Joseph Brandt | POM DPW-E | Tania Leisten | USAG PoM Section 7 Consultation: follow up from USAG submittal | Collect documents from USFWS fileshare: review matrix and other attachments; schedule site visit to PoM | Tania Leisten and Patricia Goodman, I completed my review of the U.S. Army's Presidion of Monterey Programmatic Biological Assessment (PBA) and Integrated Natural Resource Management Plan (INRMP). Attached is a comment matrix spreadsheet. I used an Excel spreadsheet for the comment matrix which has two tabs, titled PBA and INRMP. My comments for each document can be found in each of the respectively titled tabs. There are four topics related to the INRMP and PBA that my comments touch on but I'd like to more generally discuss: 1. The first topic relates to INRMP activities vs. activities that we'd consider as mitigation for PBA projects. Three of the stated guiding principles of the INRMP are: * Identify where natural resources and operational actions that compromise the function and composition of ecosystems and develop remedies through adaptive management. * Sustain and enhance healthy, terrestrial, and aquatic habitats that provide services and values in an ecosystem. * Assess, sustain, and enhance the health and habitats of fish and wildlife populations in a manner consistent with the military mission and security constraints To achieve the intent of these guiding principles the INRMP should clearly specify activities that are related to mitigating the impacts that result from the operational actions (such as those described in the PBA) and separately specify activities that are meant to assess, sustain, and enhance habitats or wildlife populations. The PBA should quantify impacts to listed species and their habitat so that appropriate levels of mitigation can be determined. This also would allow you to demonstrate in the INRMP where you are mitigating for adverse effects to listed species as a result of operational activities per section 7(a)(2) of the Endangered Species Act (ESA), and where you are carrying out conservation activities to manage and enhance habitat for listed species per section 7(a)(1) of the ESA and the intent of the Sikes Act. For permanent impacts to habitat for listed species or loss of individuals, we recommend a 3 to 1 mitigation ratio. Temporary and inadvertent impacts should result in no-net loss to the resource. If the INRMP objectives for listed species and habitat are specific, measurable, achievable, relevant, and time-based (SMART) we should easily be able determine that you are meeting these guiding principles.
2022-06-13 | Email | Ventura | Joseph Brandt | POM DPW-E | Tania Leisten | USAG PoM Section 7 Consultation: follow up previous email sent | Collect documents from USFWS fileshare: review matrix and other attachments; schedule site visit to PoM
2022-06-28 | Email | NA | NA | POM DPW-E | April Andujar | INRMP Response to Comments: email from HDR | Set up a conference call with USFWS to discuss the comments received on the INRMP. | HDR submitted response to USFWS comments to INRMP draft.
2022-09-01 |  | NA | NA |  |  | CDFW Signs INRMP
2022-09-23 | Email | NA | NA | POM DPW-E | Tania Leisten | email from HDR re: Final INRMP |  | We are ready to submit the Final INRMP with responses to USFWS comments. The response to comments spreadsheet was reviewed and approved by Patty a week or so ago. As a reminder, CDFW has already provided their signature and the next step is to request the same from USFWS. Finally, you all would then get the necessary internal signatures.
2022-11-10 | Email | NA | NA | POM DPW-E | Tania Leisten | HDR FY21 Task Order POP Extension & USFWS Mtg | Schedule site visit w/ Joseph Brandt | HDR - Kate Crosthwaite email re: TO extension and setting up at meeting with Joseph Brandt
2022-11-18 | Email | NA | NA | POM DPW-E | Tania Leisten | USFWS comment matrix responses submitted 2022-10-28, site visit w/ Joseph Brandt, Patty Goodman, Kate (HDR)
2022-11-18 | Meeting-InPerson | Ventura | Joseph Brandt | POM DPW-E | Patty Goodman | Site visit w/ HDR Kate C.
2023-01-23 | Meeting-Teams | Ventura | Leilani, Joseph, Todd | POM DPW-E | Julia Parish | Meet and Greet, discuss INRMP | - Todd to send Piperia dispersal study and the most recent 5yr Review document – DONE; - Julia to send 2022 species reports – DONE;
- Julia to look at INRMP comments and responses, investigate if POM NR is able to update INRMP. – DONE. USAG POM has spent all allocated funding for INRMP drafting & updating;
- Julia to attempt to find the potential LMV wetland area. – DONE. I was able to go out to the LMV site with the HDR contractor, Kate Crosthwaite and found the site. I am hoping to secure funding for wetland planning level surveys in future funding years;
- Julia & Todd coordinate a site visit to the POM complex in 2023. TODD - just let me know when a site visit works for your schedule.
2023-02-21 | Email | Ventura | Leilani, Joseph, Todd | POM DPW-E | Julia Parish | Follow up on Action Items from 01/23 Intro Mtg |  | Action items from the 01/23 discussion include: Todd to send Piperia dispersal study and the most recent 5yr Review document – DONE
Julia to send 2022 species reports – DONE
Julia to look at INRMP comments and responses, investigate if POM NR is able to update INRMP. – DONE. USAG POM has spent all allocated funding for INRMP drafting & updating.
Julia to attempt to find the potential LMV wetland area. – DONE. I was able to go out to the LMV site with the HDR contractor, Kate Crosthwaite and found the site. I am hoping to secure funding for wetland planning level surveys in future funding years.
Julia & Todd coordinate a site visit to the POM complex in 2023. TODD - just let me know when a site visit works for your schedule!
I will be in the Santa Barbara ¦ Ventura area this Friday if you would like to meet in person! I am attending the Santa Barbara Botanical Garden annual symposium on Saturday.
2023-02-21 | Email | Ventura | Leilani, Joseph, Todd | POM DPW-E | Julia Parish | Follow up on Action Items from 01/23 Intro Mtg |  | Hello Leilani, Joseph, and Todd,
I have read through the comments provided by USFWS regarding the USAG POM INRMP under draft. Apologies for the delayed response from our meeting! After reading over the draft INRMP and comments ¦ responses provided, I wanted to confirm that you all had access to and reviewed the information in the USAG POM INRMP Appendix B (attached here)? It seems to address comments and concerns mentioned in the attached comments and during our discussion, including planning for Piperia yadonii seed collection and seed dispersal (see Appendix B INRMP Issue # POM-TES-1.10 pg B-12).
Since I was not a part of previous discussions, I also was hoping to confirm that you all are aware that the USAG POM's most current INRMP is from 2008? I was surprised to learn that is the most current version, so I wanted to make sure you all knew that as well. Julia
2023-03-01 | Email | Ventura | Leilani, Joseph, Todd | POM DPW-E | Julia Parish | Communication preferences, timelines, PBA Status |  | Hi Leilani, Joseph, and Todd, I wanted to follow up on the emails I sent last week, and our POM INRMP and PBA discussion from January.
2023-03-07 | Email | Ventura | Leilani, Joseph, Todd | POM DPW-E | Julia Parish | Re: Communication preferences, timelines, PBA Status |  | Hi Julia, Joseph and I will review your questions together and get back to you no later than March 13, COB. I really appreciate your email, and your collaborative effort to move the INRMP and PBO forward.