## 23-INRMP
Start_Date | End_Date | Duration | CommunicationType | USFWS_RegionalLeadOffice | USFWSParticipantName | USAG_DirectorateLead | USAG_ParticipantName | Deliverable | Subject
2020-07-31 | 2020-07-31 | 0 | Email | NA | NA | POM DPW-E | April Andujar | PoM INRMP Revision Initation | HDR Draft Agency INRMP Development notificiation to CDFW USFWS
2020-07-31 | 2021-11-21 | 478 | Other |  |  | POM DPW-E | April Andujar | Draft INRMP Development
2020-09-15 | 2020-09-15 | 0 | Meeting-Teams | NA | NA | POM DPW-E | April Andujar | USAG Internal INRMP Revision Kick Off Mtg | INRMP Revision Internal Kickoff Meeting w/ Army
2020-12-14 | 2021-01-14 | 30 | Email | Ventura | Mark Ogonowski | POM DPW-E | April Andujar | USFWS INRMP Revision Notification & Kick Off Meeting Schedule | PoM INRMP Revision Announcement & schedule meeting
2021-01-14 | 2021-01-14 | 0 | Meeting-Teams | Ventura | Leilani, Joseph, Todd | POM DPW-E | April Andujar | USAG External INRMP Revision Kick Off Mtg | PoM INRMP Revision Kick Off Meeting
2021-05-26 | 2021-05-26 | 0 | Email | Ventura | Joseph Brandt | POM DPW-E | April Andujar | USFWS INRMP draft Status Update Request | PoM INRMP Meeting - USFWS inquiry on INRMP Status
2021-11-17 | 2021-11-17 | 0 | Email | Ventura | Joseph Brandt | POM DPW-E | April Andujar | PoM NR Mgr Departure Notice
2021-11-21 | 2021-11-21 | 0 | Email | Ventura | Joseph Brandt | POM DPW-E | April Andujar | PoM INRMP draft submittal | Submittal of PoM INRMP draft
2021-11-21 | 2022-05-27 | 186 | Other | NA | NA | POM DPW-E | April Andujar | USFWS INRMP Review
2021-11-21 | 2021-11-21 | 0 | Other | NA | NA | POM DPW-E | April Andujar | USACE IMCOM IRNMP Comment Matrix | USACE IMCOM IRNMP Comment Matrix
2021-12-02 | 2021-12-02 | 0 | Memo | NA | NA | POM DPW | Jack Poling | INRMP Submittal to CDFW | INRMP Submittal to CDFW
2021-12-05 | 2021-12-05 | 0 | Other | NA | NA | POM DPW-E | April Andujar | PoM NR Mgr - April's Last Day | PoM NR Mgr - April's Last Day
2022-01-06 | 2022-01-06 | 0 | Email | NA | NA | POM DPW-E | Tania Leisten | HDR INRMP Revision Contract Extension | USACE FY20 HDR Contract POP Extension W9127820F0190
2022-03-25 | 2022-03-25 | 0 | Email | Ventura | Leilani Takano | POM DPW-E | Tania Leisten | USFWS INRMP Review Update | USAG PoM Section 7 Consultation: INRMP PBA Comments
2022-06-14 | 2022-06-14 | 0 | Letter-Digital | NA | NA | UNK | UNK | INRMP Signed by CDFW | CDFW Signed INRMP
2022-05-27 | 2022-05-27 | 0 | Email | Ventura | Joseph Brandt | POM DPW-E | Tania Leisten | USFWS INRMP Review & Comments Submittal | USFWS INRMP Review & Comments
2022-05-27 | 2022-10-28 | 154 | Email | Ventura | Joseph Brandt | POM DPW-E | Tania Leisten | PoM Response to USFWS INRMP Comments Submitted | INRMP Comment Matrix to USFWS
2022-05-30 | 2022-09-23 | 116 | Email | NA | NA | POM DPW-E | Tania Leisten | Final INRMP completed | email from HDR re: Final INRMP
2022-10-28 | 2022-10-28 | 35 | Other | Ventura | Joseph Brandt | POM DPW-E | Patty Goodman | PoM INRMP Final submitted to USFWS | signed by CDFW
2022-11-18 | 2022-11-18 | 0 | Meeting-InPerson | Ventura | Joseph Brandt | POM DPW-E | Patty Goodman | USFWS PoM Site Visit | Site visit w/ HDR Kate C.
2022-12-05 | 2022-12-05 | 0 | Other | NA | NA | POM DPW-E | Julia Parish | PoM NR Mgr - Julia's First Day | PoM NR Mgr - Julia's First Day
2023-01-23 | 2023-01-23 | 0 | Meeting-Teams | Ventura | Leilani, Joseph, Todd | POM DPW-E | Julia Parish | New PoM NR Mgr & USFWS INRMP Meeting | Meet and Greet, discuss INRMP